## Tasks
ID | Task Name | Start | Finish | Duration (days) | Resources | % Complete | RAG | Comment
1 | Project | 2025-11-06 | 2025-12-04 | 28 |  | 8
2 | Requirements | 2025-11-06 | 2025-11-09 | 3 |  | 50
3 | capture requirements | 2025-11-06 | 2025-11-09 | 3 | Alice | 50 | Green | Interviews with stakeholders
4 | Design | 2025-11-09 | 2025-11-11 | 2
5 | Low Level Design | 2025-11-09 | 2025-11-11 | 2 | Andy Mcarthy |  | Green | with signoff
6 | Build | 2025-11-11 | 2025-11-16 | 5
7 | develop software | 2025-11-11 | 2025-11-16 | 5 | Bob Smith |  | Green | agile development
8 | Test | 2025-11-16 | 2025-11-25 | 9
9 | test plan | 2025-11-16 | 2025-11-19 | 3 | Charlie Brown |  | Green
10 | system testing | 2025-11-19 | 2025-11-23 | 4 | Charlie Brown |  | Green
11 | user acceptance testing | 2025-11-23 | 2025-11-25 | 2 | Diana Prince |  | Green
12 | Testing Complete | 2025-11-25 | 2025-11-25 | 0 |  |  | Green
13 | Deploy | 2025-11-25 | 2025-11-27 | 2
14 | go no go decision | 2025-11-25 | 2025-11-26 | 1 | Eve Adams |  | Green
15 | go live | 2025-11-26 | 2025-11-27 | 1 | Frank Castle |  | Green | final decision
16 | Deploy Complete | 2025-11-27 | 2025-11-27 | 0 |  |  | Green | product now live
17 | Support | 2025-11-27 | 2025-12-04 | 7
18 | hypercare | 2025-11-27 | 2025-12-04 | 7 | Grace |  | Green | 24/7 support provided for 1 week

## Milestones
Milestone | Type | Date
Requirements | Phase | 2025-11-09
Design | Phase | 2025-11-11
Build | Phase | 2025-11-16
Test | Phase | 2025-11-25
Testing_Complete | Milestone | 2025-11-25
Deploy | Phase | 2025-11-27
Deploy_Complete | Milestone | 2025-11-27
Project | Phase | 2025-12-04
Support | Phase | 2025-12-04

## Resources
Resource | Total Hours | Tasks Assigned
Alice | 24 | capture_requirements
Andy | 16 | Low_Level_Design
Bob | 40 | develop_software
Charlie | 56 | test_plan, system_testing
Diana | 16 | user_acceptance_testing
Eve | 8 | go_no_go_decision
Frank | 8 | go_live
Grace | 56 | hypercare