## Tasks
ID | Phase | Task Name | Start | Finish | Duration (days) | Resources | % Complete | Comment
|  | --- | 2025-11-06 | 2025-11-07 | 1 |  | 0
|  | title: Sample Project | 2025-11-07 | 2025-11-08 | 1 |  | 0
|  | project manager: Kevin | 2025-11-08 | 2025-11-09 | 1 |  | 0
|  | Resources: | 2025-11-09 | 2025-11-10 | 1 |  | 0
|  | - | 2025-12-26 | 2025-12-27 | 1 |  | 0
|  | Holidays: | 2025-12-27 | 2025-12-28 | 1 |  | 0
|  | Requirements | 2025-11-06 | 2025-11-07 | 1 |  | 50
| Requirements | capture requirements | 2025-11-06 | 2025-11-07 | 1 | Alice | 50 | Interviews with stakeholders
|  | Design | 2025-11-06 | 2025-11-07 | 1 |  | 0
| Design | Low Level Design | 2025-11-06 | 2025-11-07 | 1 | Andy | 0 | with signoff
|  | Build | 2025-11-06 | 2025-11-07 | 1 |  | 0
| Build | develop software | 2025-11-06 | 2025-11-07 | 1 | Bob | 0 | agile development
|  | Test | 2025-11-06 | 2025-11-07 | 1 |  | 0
| Test | test plan | 2025-11-06 | 2025-11-07 | 1 | Charlie | 0
|  | Deploy | 2025-11-06 | 2025-11-07 | 1 |  | 0
| Deploy | go-no-go decision | 2025-11-06 | 2025-11-07 | 1 | Eve | 0
|  | Support | 2025-11-06 | 2025-11-07 | 1 |  | 0
| Support | hypercare | 2025-11-06 | 2025-11-07 | 1 | Grace | 0 | 24/7 support provided for 1 week

## Milestones
Milestone | Type | Date
Requirements | Phase | 2025-11-07
Design | Phase | 2025-11-07
Build | Phase | 2025-11-07
Test | Phase | 2025-11-07
Deploy | Phase | 2025-11-07
Support | Phase | 2025-11-07

## Resources
Resource | Total Hours | Tasks Assigned
Alice | 8 | capture requirements
Andy | 8 | Low Level Design
Bob | 8 | develop software
Charlie | 8 | test plan
Eve | 8 | go-no-go decision
Grace | 8 | hypercare